## Summary
Group Name | PL2 - PetPeople |  | Priority
|  |  | Name | Description | Number
Students | 2019216077 - Edgar Duarte |  | Must Have |  | 15
| 2019220082 - Sofia Neves |  | Should Have |  | 16
| 2019219581 - Tatiana Almeida |  | Could Have |  | 6
0
Architecture Significant Requirements |  |  | Architecture elements
ID | Type | Number | ID | Type | Number
AC | Actor | 8 | COMP | Component | 44
UC | Use Case | 15 | CONN | Connector | 0
QAS | Quality Atribute Scenario | 22 |  |  | 0
TC | Technical Constraint | 3 |  |  | 0
BC | Business Constraint | 5 |  |  | 0
|  | 0 |  |  | 0
|  | 0 |  |  | 0
|  | 0 |  |  | 0
|  | 0 |  |  | 0
|  | 0 |  |  | 0
Tipe | Status | Number
Risks | Open | 5
| Closed | 0
Issues | Open | 0
| Closed | 0
Assumptions | Open | 1
| Closed | 0
Dependencies | Open | 6
| Closed | 0

## Issues
Project Name: |  | PL2 - PetPeople |  |  |  | 1-No action, 2 clarify…
Issues Register
Last Reviewed: {date}
Something that is going wrong on your project and needs to be managed. Failure to manage issues may result in a poor delivery or even failure. The log includes a description of each issue, the impact it is having, its seriousness and actions needed to contain and remove it.
ID | Date Raised | Issue Description | Impact Description | Impact | Priority | Mitigation Plan | Owner | Status | Comments
1
2
3
4
5
6
7
8
9
10
Note on F5: Scoring: High Medium Low
Note on G5: Scoring: High Medium Low

## Risks
Project Name: |  | PL2 - PetPeople
Risk Register
Last Reviewed: |  | {date}
Events that will have a negative impact on your project if they occur. Risk refers to the combined likelihood the event will occur and the impact on the project if it does occur. If the likelihood of the event happening and impact to the project are both high, you identify the event as a serious risk. The log includes a description of each risk, analysis and a plan to manage it.
ID | Date Raised | Risk Description | Likelihood | Impact | Severity | Mitigation Plan | Owner | Status | Date Closed
1 |  | Application might not be able to scale to the amount of requests by users. The number of initial MongoDB shards and Amazon Elastic Block Store may not be suficient | 1 | 5 | 5 | Monitor resource utilization and if it forecasted that there will be a need for more resources, add more shards or increase the size of the Elastic Block | Database Admin | Open
2 |  | The censor system needs to be tested in the context of animal photos, seeing that Rekognition's documentation is not clear if it detects animal cruelty and abuse. This needs to be verified for a safe and secure platform utilization | 3 | 5 | 15 | Initially have many active admins that respond to reported content. An admin's decision should be informed to the Censor System, so that it can evolve. Once the efficiency of the algorithm has been calculated, the number of admins should be adjusted accordingly. If there are a lot of false positives, then we need to change the Censor System's dataset. If there are a lot of false negatives, then we need more data. | Tester | Open
3 |  | The architecture may lack streamlined deployment processes, leading to a complex deployment process | 5 | 3 | 15 | Configure CI/CD pipelines to automate the deployment testing process. | Developer | Open
4 |  | High mobile data usage. Due to the complexity behind the features, it is somewhat likely that the application has a high mobile data usage | 3 | 3 | 9 | Reduce the quality of images and videos in order to reduce the data needed to load them | Developer | Open
5 |  | There might be performance bottlenecks in the fetching of data. There needs to be verification of the efficiency of the Inteligent Model and its performance in terms of speed. | 5 | 1 | 5 | Have a defined set of preloadable content (may be old posts that are still in cache) that loads in case the Inteligent System is taking too long. | Developer | Open |  | 3
Note on E5: Scoring: Low = 1 Medium = 3 High = 5
Note on F5: Scoring: Low = 1 Medium = 3 High = 5

## Assumptions
Project Name: |  | PL2 - PetPeople
Assumptions
Last Reviewed: {date}
Any factors that you are assuming to be in place that will contribute to the successful result of your project. The log includes details of the assumption, the reason it is assumed and the action needed to confirm whether the assumption is valid.
ID | Date Raised | Assumption Description | Reason for Assumption | Action to Validate | Impact if Assumption Incorrect | Status
1 |  | We assume that 1000 ad impressions lead to 8$ of revenue. | Public available data. We need to have at least this amount to make the application profitable | Check ad revenue analytics | The application might not be profitable | Open
2
3
4
5
6
7
8
9
10

## Dependencies
Project Name: |  | PL2 - PetPeople
Dependencies
Last Reviewed: {date}
Any event or work that are either dependent on the result of your project, or your project will depend on. The log captures who you are dependent on, what they should deliver and when. It may also include who is dependent on you.
ID | Date Raised | Dependency Description | Location | Deliverables | Delivery Date | Importance | Status | Comments
1 |  | The system is dependent on the external payment systems. If they fail, payments may become unavailable in the platform, meaning lost income for the platform. Due to this, it is a dependency of great importance |  |  |  | High | Open
2 |  | The system is dependent on the Censor System. If it fails, NSFW content might appear in the application, subjecting minors to adult content. This makes it a dependency of great importance |  |  |  | High | Open
3 |  | The system is depends on Google Analytics to obtain user data. If this system fails, the application might lose access to usefull user data. Even so, seeing that the application has its own database that contains its own content, it should not be a big issue if it fails |  |  |  | Low | Open
4 |  | The system depends on the external email system functioning. If it goes down, users might have trouble signing up and recovering their passwords. Some other notifications will also be lost. As such, it is a dependability of medium importance |  |  |  | High | Open
5 |  | The system depends on the external SMS system for 2FA operations. This means that if this service fails, users that have 2FA activated will become unable to login to their acount. Due to this, it has a high importance |  |  |  | Low | Open
6 |  | The system is dependent on the app notification system to send alerts to users when they are not online. It is not responsible for sending notifications of login or transactions, so its failure is not very critical. |  |  |  | High | Open
7
8
9
10
Note on H5: Scoring: High Medium Low

## ARCH
PL | PL2 - PetPeople
ID | Name | Type | Description | Comments | NumberRelations
A1 | PetPeople App | COMP | The System |  | 4
A2 | Payments System | COMP | External Payments API |  | 0
A3 | App Notification System | COMP | Responsible for sending notifications in offline mode |  | 0
A4 | Censor System | COMP | External Censor System |  | 0
A5 | Analytics System | COMP | External Analytics System |  | 0
A6 | Email System | COMP | Responsible for sending emails to users (can be authentication or informational emails). |  | 0
A7 | SMS System | COMP | Responsible to send mobile messages to users, for 2FA purposes |  | 0
A8 | PetPeople Android App | COMP | Android mobile App |  | 0
A9 | PetPeople Web App | COMP | Web App for Microsoft Edge, Firefox, Chrome, Brave, Opera, Safari, Tor and Samsung Internet |  | 0
A10 | PetPeople iOS App | COMP | IOS mobile App |  | 0
A11 | Web API | COMP | Backend Web API |  | 0
A12 | Mongoose (ODM) | COMP | Library to use MongoDB with Express.js |  | 0
A13 | Web API for APP | COMP | PetPeople App API |  | 0
A14 | PetPeople UI | COMP | Responsible for creating and presenting the UI to the user
A15 | AA Controller | COMP | Responsible for managing user authorization and authentication |  | 0
A16 | Content Controller | COMP | Responsible for handling content like information hub, posts, products, etc |  | 0
A17 | Analytics Controller | COMP | Responsible for updating and retrieving analytical data of users |  | 0
A18 | Notification Controller | COMP | Responsible for handling notifications |  | 0
A19 | Message Controller | COMP | Responsible for handling messages from users |  | 0
A20 | Report Controller | COMP | Responsible for handling reports |  | 0
A21 | Payment Controller | COMP | Responsible for handling payments |  | 1
A22 | Socket Componnent | COMP | Responsible of controlling the sockets of the clients that will try to access the server
A23 | (AA) Sign In Controller | COMP | Allow for users to sign in to the platform
A24 | (AA) Register Controller | COMP | Allow for users to register to the platform
A25 | (AA) Account Recovery Controller | COMP | Allows users to reset their lost credentials
A26 | (AA) Security Component | COMP | Responsible for validating user authentication and account register
A27 | (CC) Request Orchestrator | COMP | Responsible for handling specific requests, like loading a chosen photo or obtaining a list of products
A28 | (CC) Upload Manager | COMP | Responsible for uploading the content to the database and to the censor system
A29 | (CC) Feed Manager | COMP | Responsible for showing the user their feed
A30 | (CC) Bandwidth Controller | COMP | Responsible for adjusting video and photo quality according to user's bandwidth
A31 | (CC) Search Controller | COMP | Responsible for handling search requests
A32 | (CC) Censor Controller | COMP | Responsible for deleting any NSFW content from the app
A33 | (CC) Intelligent Fetch Model | COMP | Responsible for updating the feed of a user
A34 | (CC) Interaction Controller | COMP | Controls interactable components, like accounts and posts
A35 | (FM) Marketplace Feed Component | COMP | Responsible to manage the marketplace feed
A36 | (FM) Social Network Feed Component | COMP | Responsible to manage the social network feed
A37 | (FM) Information Hub Feed Component | COMP | Responsible to manage the information hub feed component
A38 | (IC) Account Controller | COMP | Responsible for handling interaction on user accounts
A39 | (IC) Post Controller | COMP | Responsible for handling interaction on photos or videos
A40 | (IC) Information Controller | COMP | Responsible for handling interaction on pets news, advices or specific information
A41 | (IC) Feature Controller | COMP | Responsible for displaying the correct features
A42 | (IC) Product Controller | COMP | Responsible for handling interaction on products from the marketplace
A43 | (FM) Feature Orchestrator | COMP | Selects which features will be shown to each controller
A44 | (FM) Follow Component | COMP | Responsible for following other accounts
A45 | (FM) Share Component | COMP | Responsible for sharing content
A46 | (FM) Like Component | COMP | Responsible for liking content
A47 | (FM) Reply Component | COMP | Responsible for replying to content
A48 | (FM) Buy Component | COMP | Responsible for buying products through the marketplace
A49 | (RC) Permissions Handler | COMP | Responsible for checking a user's permissions
A50 | (RC) Report Logger | COMP | Saves all reports for later handling by administrators
A51 | (RC) Decision Controller | COMP | Allows admins to act upon reports (ignore them, ban or warn the users)
A52 | (MC) Message Server | COMP | Responsible for receiving and sending messages to clients and saving the message data to the database
A53 | (MC) Secure Communication Component | COMP | Responsible for encrypting the message and making sure no one eavesdrops on it
A54 | (MC) Client Communicator Component | COMP | Responsible for sending and receiving messages from the middleware
A55 | (MC) Server Message Sender | COMP | Responsible for correctly sending them to users
A56 | (PCC) Paymetns Proxy | COMP | Allows users to pay with differente methods
A57 | (PCC) PayPal Payments | COMP | Responsible for allowing PayPal payments
A58 | (PCC) CC Payments | COMP | Responsible for allowing Credit Card payments
A59 | (PCC) Multibanco Payments | COMP | Responsible for allowing Multibanco
A60 | (PCC) MBWay Payment | COMP | Responsible for allowing MBWay payments
A61 | (PCC) Payments Facade | COMP | Responsible for the correct handling of a transaction
A62 | (PF) Payment request orchestrator | COMP | Selects the appropriate response according to the requests
A63 | (PF) Payments authentication | COMP | Responsible for authenticating a payment
A64 | (PF) Transaction Controller | COMP | Responsible for setting up a transaction
A65 | (PF) Communication Controller | COMP | Responsible for communicating with the external payment service
A66 | (NCC) Notification Orchestrator | COMP | Responsible for selecting the correct action according to the requests
A67 | (NCC) Email Component | COMP | Responsible for sending emails
A68 | (NCC) Platform Notification System | COMP | Responsible for alerting the user of new notifications
A69 | (NCC) SMS Component | COMP | Responsible for sending SMS
A70 | (ComC) Out communications controller | COMP | Responsible for sending messages the the external system
A71 | (ComC) In communications controller | COMP | Responsible for receiving messages from the external system
A72 | (Dep) AWS Load Balance | COMP | Load balancing service on the cloud
A73 | (Dep) Replica Controller | COMP | Are a group of mongod processes that maintain the same data set. Responsible for providing redundancy and high availability
A74 | (Dep) Version Control System | COMP | Responsible for managing different versions of the platform, including the ability to rollback to previous versions in case an update fails or causes issues
A75 | (Dep) Database Orchestrator | COMP | Responsible for selecting the correct database to use
A76
A77
A78
A79
A80
A81
A82
A83
A84
A85
A86
A87
A88
A89
A90
A91
A92
A93
A94
A95
A96
A97
A98
A99
A100
A101
A102
A103
A104

## ASR
PL2 - PetPeople
Risk Register
Last Reviewed: | {date}
ID | Type |  | Name | User story | Requirement | Priority | Scenarios | Comments | Validation | NumberRelations
A1 | AC |  | Arquitect | [6 empty] | 0
A2 | AC |  | Client
A3 | AC |  | Developer | [6 empty] | 0
A4 | AC |  | Guest
A5 | AC |  | Shopkeeper | [6 empty] | 0
A6 | AC |  | System | [6 empty] | 0
A7 | AC |  | User | [6 empty] | 0
A8 | AC |  | Veterinarians | [6 empty] | 0
FR-1 | UC | Authentication | Log in | As a User, I want to be able to log in into my account in order to see its contents | The system must have a log in system | MUST HAVE |  |  |  | 0
FR-2 | UC |  | Register account | As a Guest, I want to be able to register a new account | The system must allow creation of new accounts | MUST HAVE |  |  |  | 0
FR-3 | UC | Search engine | Find other users | As a User, I want to be able to search for other usernames so that I can see other peoples' profiles | The system must allow users to search for other peoples' profiles | MUST HAVE |  |  |  | 0
FR-4 | UC |  | Find veterinarians | As a User, I want to be able to see which veterinarians are available and what their specialties are so I can make an informed choice | The system could allow users to find veterinarians and their information | COULD HAVE |  |  |  | 0
FR-5 | UC |  | Information | As a User, I want to be able to see information about animals so I can stay informed | The system could allow users to find information about animals | COULD HAVE |  |  |  | 0
FR-6 | UC |  | Find shelters | As a User, I want to be able to see which shelters are available so I can adopt a pet | The system could allow users to find shelters and their information | COULD HAVE
FR-7 | UC | Social network | Post content | As a User, I want to be able to post content of my pet so that I can show people my pet | The system should allow users to post content about their pet | MUST HAVE |  |  |  | 0
FR-8 | UC |  | React to content | As a User, I want to be able to react to content so that I can show people my love or thoughts | The system should allow users to react to content | MUST HAVE |  |  |  | 0
FR-9 | UC |  | Message other users | As a User, I want to be able to communicate with other users, especially with shopkeepers when I am buying a product | The system should allow users to send messages to each other, through a built-in messaging app | SHOULD HAVE |  |  |  | 0
FR-10 | UC |  | Report | As a User, I want to be able to report content or accounts I deem innapropriate | The system could allow users to report users and/or content | COULD HAVE
FR-11 | UC |  | Block an account | As a User, I want to be able to block accounts, so I do not see their contents and they do not see mine | The system could allow users to block other users | COULD HAVE
FR-12 | UC | Marketplace | Marketplace | As a User, I want to be able to buy things for my pet so that it has a better quality of life | The system should be able to handle transactions | SHOULD HAVE |  |  |  | 0
FR-13 | UC |  | Sell items | As a Shopkeeper, I want to be able to sell my items so that I can make profit | The system should allow shopkeepers to sell their items | SHOULD HAVE |  |  |  | 0
FR-15 | UC | Profile | Edit profile | As a User, I want to be able to edit my profile | The system should allow the editing of a user's profile | MUST HAVE
FR-14 | UC |  | Attribution of categories | As a User, I want to be able to discern if I am a shopkeeper and/or veterinarian so that other users know my field of work | The system should allow the user to choose their categorie(s) | SHOULD HAVE |  |  |  | 0
QA-1 | QAS |  | Correct emails | As a Guest, I want to be sure my email is correct so that I may verify it | The system should verify if an email is valid or not. If it is not then the account being created should be rejected | MUST HAVE | A guest creates an account when the system is in normal operation. The Email Validation System responds by sending a confirmation email to the email address if it is valid. If it is not, it asks the guest for a new email. To measure the response, it checks if the system can identify correctly, at least 100% of fake email accounts. |  |  | 1
QA-2 | QAS |  | Secure payment | As a User, I want to have secure payments so my money is received by the correct seller | The system should send transactions to the correct seller without any eavesdroppers | MUST HAVE | The user makes a transaction when the system is in normal operation. The Transaction System then responds by sending the transaction to the correct seller. To measure the response, it checks if 100% of the transaction are authentic. |  |  | 1
QA-3 | QAS |  | Secure messaging | As a User, I want to have secure messages so that no one else intercepts my communications and extracts its contents | The system should have a secure messaging system | MUST HAVE | The user sends a private message to another when the system is in normal operation. The Messaging system then responds by safely sending the message encrypted to the other user. To measure the response, it checks if no messages are ever intercepted by unwanted third parties. |  |  | 1
QA-4 | QAS |  | Easy maintenance (Modifiability) | As a Developer, I want to be able to easily mantain and add features to the existing application | The system should be designed to allow for easy and efficient maintenance, including updates, bug fixes, and enhancements. | SHOULD HAVE | A developer releases an update when the system is in normal operation. The Deployment Control System responds with the modification being deployed on the different machines and to measure the response, it checks if the software was updated without making the service go down for users. |  |  | 1
QA-5 | QAS |  | Documentation (Modifiability) | As a Developer, I want to easily be able to understand foreign code | The system should have good documentation to ease mantainability and modifications of the application | SHOULD HAVE |  |  |  | 1
QA-6 | QAS |  | Modularity (Modifiability) | As a Client, I want the system to be modular to facilitate the addition, removal, or replacement of modules without affecting other parts of the system. | The system should be designed to be modular | SHOULD HAVE | The developer adds, removes or replaces a module when the system is in normal or update operation. The system responds by performing the selected action and to measure the response, it checks if the action was completed without any downtime and interference from other modules
QA-7 | QAS |  | Secure password | As a Guest, I want to be able to register a new account with a secure password | The system should be able to ensure that a given password is secure or not | COULD HAVE | A guest creates an account when the system is in normal operation. The Password Validation System responds by checking the strength of the inputted password. If it is not strong enough, it requests the guest for a new password. To measure the response, it checks if all the passwords accepted are strong passwords. |  |  | 1
QA-8 | QAS |  | Recover access | As a User, I want to be able to recover my account access after I lose my credentials | The system should allow the user to recover the access to their account after they lose their password, username or email | MUST HAVE | A user requests to recover access to an account when the system is in normal operation. The Authentication/Authorization Service then responds by sending details to the user on how to proceed with the account recovery. To measure the response, it checks if the information was sent to the user in less than 1 minute.
QA-9 | QAS |  | Multi-language | As a User, I want to have the option of viewing the platform in different languages | The system should have multi-language integration | SHOULD HAVE | A user wants to change the page's language when the system is in normal operation. The Language System responds by altering the page's content according to the preferences chosen by the user. To measure the response, it checks if the page's content changes correctly and in less than 10 seconds.
QA-10 | QAS |  | Up time (Availability) | As a Client, I want the platform to be online 99% of the time | The system should be up at least 99% of the time per year | SHOULD HAVE | The system's software fails/crashes in normal operation. The system responds by entering a previous safe state. To measure the response, it checks if the restart occured in less than 1 minutes after the initial crash.
QA-11 | QAS |  | Cardholder information (Confidentiality) | As a User, I want my card and banking informations to not be stored by the platform, in order to preserve my privacy | The system should not store any of the banking information inserted by the User when a transaction is made | MUST HAVE | A user performs a transaction in normal operation. The transaction system responds by completing the transaction without storing any of the user's banking data. To measure the response, it checks the database for any storage of the user's banking information data.
QA-12 | QAS |  | Video loading time (Efficiency) | As a User, I want the videos to load quickly | The system should load the videos in less than 2.5 seconds | SHOULD HAVE | The user finds a video with the system in normal operation. The system responds by automatically starting the video. To measure the response, it checks if the starting time was less than 2.5 seconds.
QA-13 | QAS |  | Transaction time (Usability) | As a User, I want to receive feedback quickly from my transactions | The system should abort any transaction that takes longer than 30 seconds. | SHOULD HAVE | The user makes a transaction when the system is in normal operation. The Transaction system responds by processing the transaction and sending the user feedback about the transaction's current state. To measure the response, it checks if the transaction does not take longer than 30 seconds to be executed.
QA-14 | QAS |  | Backup of data (Integrity) | As a User I want my data to be backed up | The system should have database replication | SHOULD HAVE | The user changes its data to the system when it is in normal operation. The system responds by backing up the changes in the database. To measure its response, it checks if the data is correctly saved and it is void of corrupted information.
QA-15 | QAS |  | Censoring of adult content (Safety) | As a Client, I want my young Users to be protected against adult content | The system should bar any adult content to Users bellow 18 years old | MUST HAVE | The user uploads adult content to the system when it is in normal operation. The Content Filter System responds by deleting the content and warning the user. To measure the response, it checks if the innapropriate content was deleted in less than 1 hour.
QA-16 | QAS |  | Update rollback (Survivability) | As a User, I want the system to continue working after failed updates | The system should continue to work after failed updates | SHOULD HAVE | The system fails when trying to perform an update while the system is on normal or development operation. The system must continue to function with the latest version, prior to the update without any downtime
QA-17 | QAS |  | Sustain an annual user growth of 10% (Scalability) | As a Client, I want the system to be able to sustain an anual growth in users of 10% | The system should be able to whitstand an anual growth in users of 10% | SHOULD HAVE | A user uploads content to the system when it is running in normal operation. The system responds by handling the growth in content in a scalable and controlled manner. To measure the response, it checks if there is any downtime or side effects on the system.
QA-18 | QAS |  | Usability | As a User, I want to easily learn and use the system. | The system should follow at least 7/10 Nielson's Heuristics | SHOULD HAVE | The user navigates the interface when the system is in normal operation. The system responds by providing an interface that abides to at least 7/10 Nielson's Heuristics. To measure the response, it checks if users can navigate to the desired page in less than 10 seconds.
QA-19 | QAS |  | Verifiability | As a Arquitect, I want to design a testable application | The system should be designed so that the components can be tested in isolation | SHOULD HAVE | The testers test the system when it is in normal and testing operation. The system responds by allowing components to be tested individually, making it easier to test. To measure the response, it checks if all the components can be tested independently.
QA-20 | QAS |  | Number of transactions (Performance) | As a Client, I want the system to make as many transactions as possible | The system should be able to handle 1000 transactions a minute | MUST HAVE | Users perform transactions simultaneously when the system is in normal operation. The Transaction system responds by orchestrating the incoming transactions. To measure the response, it checks if the system can hold up to 1000 transactions per minute.
QA-22 | QAS |  | Sustain an annual content growth of at least 200% in content (Scalability) | As a Client, I want the system to be able to sustain an annual content growth of at least 200% | The system should be able to sustain an annual growth of at least 200% in content | MUST HAVE | The system receives new content under normal operation. The system responds by storing the content in the databases. To measure the response, the content's integrity is checked to see if it still exists and is correct, without loss in performance.
QA-23 | QAS |  | Number of concurrent requests (Performance) | As a Client, I want the system to handle multiple users' requests at the same time | The system should be able to handle 800 requests per second | MUST HAVE | The users perform concurrent requests while the system is in normal operation. The system responds by handling each request independently and assynchronously. To measure the response, it checks if the system can handle at least 800 requests per second.
TC-2 | TC |  | Mobile application and web browser availability | As a Client, I want to have my application available both on mobile and on a web browser | The system should be accessible to users from a mobile application and a web browser |  |  |  |  | 0
TC-3 | TC |  | Android & IOS integration | As a Client, I want to have my mobile application on both android and IOS | The system should be accessible on mobiles with Android or IOS |  |  |  |  | 0
TC-4 | TC |  | Microsoft Edge, Firefox, Chrome, Brave, Opera, Safari, Tor and Samsung Internet integration | As a Client, I want to have my web platform on my favorite web browser | The system should be accessible on Microsoft Edge, Firefox, Chrome, Brave, Opera, Safari, Tor and Samsung Internet |  |  |  |  | 0
BC-1 | BC |  | Low Funds | As a Client that is starting a business, I want to save the most I can seeing that I do not have a lot of funds | The system should not cost more than 80000€ to be built |  |  |  |  | 0
BC-2 | BC |  | Time to market | As a Client, I want the platform to be in development for, at most, 1 year | The system must be developed in, at most, 1 year |  |  |  |  | 0
BC-3 | BC |  | Limited resources | As a Client, I want to have to employ, at most, 2 developers and 1 designer in order to reduce operational costs during the development phase | The system must be developed by, at most, 2 developers and 1 designer during the development phase |  |  |  |  | 0
BC-4 | BC |  | Collection of personal data | As a Client, I want to comply to COPPA (Children's Online Privacy Protection Act) | The system must comply to COPPA's regulations
BC-5 | BC |  | Age restriction | As a Client, I want my Users to be at least 13 years old, so that I do not have problems with the law | The system must require Users to be older than 13 years old
BC-6 | BC |  | Credit Cards | As a Client, I want my Users to be able to pay using MasterCard, VIsa, MBWAY, PayPal and Multibanco | The system should allow payment with MasterCard,Visa, MBWAY and Multibanco
BC-7 | BC |  | Running Costs | As a Client, I want to have the application to be profitable | The system have a ROI of 200% in 3 years
BC-8 | BC |  | First year | As a Client, I want the system to handle as many users as possible in the first year | The system should be able to have 1 million users in the first year

## Decisions
Framework: For the framework section, we surveyed five of the most popular and widely-used frameworks: Express, Django, Ruby on Rails, Laravel and Spring. To determine which framework is best suited to our platform, we evaluated each one based on the most important scenarios.
|  |  | Scenarios | Framework | DataBase | Architecture
BC-1 | Low Funds |  | ---- | Considering that we are the developers of the platform, for cost savings and a faster development process, the best framework for us would be one with which we are familiar, such as Express and Ruby on Rails. | Considering that we will be the developers of the platform, as mentioned previously in the framework section, in order to save funds and attain a faster development, the most suitable database would be one with which we are familiar, such as MongoDB or PostgreSQL. | Layered architecture, pipelined architecture and microkernel architecture (with 5 stars) Service-based architecture (with 4 stars)
| As a Client that is starting a business, I want to save the most I can seeing that I do not have a lot of funds | The system should not cost more than 80000€ to be built
QA-23 | Number of concurrent requests (Performance) |  | The users perform concurrent requests while the system is in normal operation. The system responds by handling each request independently and assynchronously. To measure the response, it checks if the system can handle at least 800 requests per second. | Express and Spring are known for their ability to handle high traffic loads efficiently.Express is a popular Node.js framework known for its simplicity and speed, making it an excellent choice for building lightweight, high-performance applications. Spring, on the other hand, is a Java-based framework that offers a broad range of features and modules, making it suitable for building complex applications that require scalability and high performance. | Document-oriented databases are designed for high performance and scalability, and they can handle concurrent requests efficiently. They store data in a flexible, semi-structured format, making them a good fit for web and mobile applications that deal with large volumes of unstructured or semi-structured data. MongoDB, in particular, has features like sharding and replication, which allow it to scale horizontally and handle high volumes of traffic. | Event-driven architecture and space-based architecture
| User story | Requirement
| As a Client, I want the system to handle multiple users' requests at the same time | The system should be able to handle 800 requests per second
QA-22 | Sustain an annual content growth of at least 200% in content (Scalability) |  | The system receives new content under normal operation. The system responds by storing the content in the databases. To measure the response, the content's integrity is checked to see if it still exists and is correct, without loss in performance. | Express and Django are both known for their ease of development and scalability. Express is a lightweight and flexible framework that can be easily integrated with different databases and libraries, making it a popular choice for building web applications. Similarly, Django has a well-established architecture and comes with a lot of built-in features and plugins, making it easy to develop and deploy web applications. | As we are building a social media platform that needed to store and process large amounts of user-generated content, such as photos and videos, a NoSQL database like MongoDB or Cassandra would be a better fit because it can handle large amounts of unstructured data and scale easily to meet the needs of a growing user base. | Event-driven architecture and space-based architecture
User story and Requirement | As a Client, I want the system to be able to sustain an annual content growth of at least 200% | The system should be able to sustain an annual growth of at least 200% in content
QA-20 | Number of transactions (Performance) |  | Users perform transactions simultaneously when the system is in normal operation. The Transaction system responds by orchestrating the incoming transactions. To measure the response, it checks if the system can hold up to 1000 transactions per minute. | To measure the response and ensure that the system can handle up to 1000 transactions per minute, we have to consider the concurrency and scalability features of each framework. Spring is known for its support for distributed systems and microservices, making it a good choice for building transactional systems that can handle a large volume of transactions. Express, on the other hand, can handle a high volume of requests concurrently, making it a suitable option for systems that require high concurrency. | PostgreSQL and MongoDB are strong contenders for handling high volumes of concurrent transactions, with PostgreSQL being a good choice for traditional relational workloads and MongoDB being a good choice for handling complex data structures and distributed transactions. Redis can also be a good choice for read-intensive workloads or as a caching layer, while MySQL and Oracle may not be the best options for handling high volumes of concurrent transactions. Both PostgreSQL and MongoDB have strong security features, but PostgreSQL is generally considered more secure due to its robust security architecture and features such as SSL encryption, row-level access control, and support for multiple authentication methods. In terms of scalability, MongoDB is often considered better because of its horizontal scaling capabilities and sharding feature, which allows for distributing data across multiple machines. PostgreSQL also supports horizontal scaling, but it typically requires more manual setup and configuration compared to MongoDB. | Event-driven architecture and space-based architecture
User story and Requirement | As a Client, I want the system to make as many transactions as possible | The system should be able to handle 1000 transactions a minute
QA-3 | Secure messaging |  | The user sends a private message to another when the system is in normal operation. The Messaging system then responds by safely sending the message encrypted to the other user. To measure the response, it checks if no messages are ever intercepted by unwanted third parties. | To measure the response and ensure that no messages are intercepted by unwanted third parties, you may need to consider the encryption and security features of each framework. Spring and Django are known for their strong security features, making them a good choice for building secure messaging systems. Express, Laravel, and Ruby on Rails can also be used, but you may need to add additional security features to ensure that messages are not intercepted by unwanted third parties. | PostgreSQL, MongoDB, and Oracle offer more comprehensive built-in security features, including encryption capabilities. These databases provide better options for ensuring the confidentiality and integrity of the messages. | Service-Based Architecture or a Microservices Architecture. In both of these architectures, each service is responsible for performing a specific task, and communication between services is done through APIs, which can be secured using encryption and authentication.
User story and Requirement | As a User, I want to have secure messages so that no one else intercepts my communications and extracts its contents | The system should have a secure messaging system
QA-4 | Easy maintenance (Modifiability) |  | A developer releases an update when the system is in normal operation. The Deployment Control System responds with the modification being deployed on the different machines and to measure the response, it checks if the software was updated without making the service go down for users. | Laravel includes built-in tools for deployment and server management, which can make it easier to deploy updates without causing downtime for users. Django also has a well-established deployment process, and it includes built-in tools for measuring response times and debugging performance issues. Ruby on Rails is known for its ease of deployment, and it includes built-in tools for automating deployment tasks. Spring is also well-suited for enterprise-level applications and includes built-in tools for measuring response times and debugging performance issues. | MySQL, PostgreSQL, and Oracle are likely the best choices for this scenario due to their strong support for online schema changes and high availability features. MongoDB and Redis may also be viable options depending on the specific needs of the application. | Microservices architecture would be a good fit. Microservices architecture is known for its ability to support continuous deployment and updates without affecting the overall system availability. Each microservice can be updated independently, allowing developers to release updates without affecting the rest of the system. Additionally, the architecture's decentralized nature reduces the risk of downtime, making it easier to maintain service availability during updates.
User story and Requirement | As a Developer, I want to be able to easily mantain and add features to the existing application | The system should be designed to allow for easy and efficient maintenance, including updates, bug fixes, and enhancements.
QA-6 | Modularity (Modifiability) |  | The developer adds, removes or replaces a module when the system is in normal or update operation. The system responds by performing the selected action and to measure the response, it checks if the action was completed without any downtime and interference from other modules | To measure the response and ensure that the selected action was completed without downtime and interference from other modules, you may need to consider the modularity and robustness of each framework. Spring, Django, Laravel, Express, and Ruby on Rails all offer modularity and flexibility, making it easy to add, remove, or replace modules without causing downtime or interfering with other modules. However, the specific approach to module management and dependency injection may differ between frameworks. | For example, PostgreSQL has a well-developed transaction management system that allows for atomicity, consistency, isolation, and durability (ACID) compliance. This means that if a module is added, removed, or replaced in PostgreSQL, the system can ensure that the action is performed correctly without any interference from other modules. Similarly, MongoDB also has a flexible and scalable architecture that can handle module additions, removals, or replacements without causing any downtime or interference. However, MongoDB does not support ACID transactions, which means that data consistency might not be guaranteed in some cases. | A microservices architecture would be a good fit. With a microservices architecture, each module is deployed as a separate service, allowing for independent development and deployment of modules. This can help ensure that adding, removing, or replacing a module doesn't result in downtime or interference from other modules. Additionally, the modular nature of a microservices architecture makes it easier to scale individual components and update them independently, further reducing the risk of downtime or interference.
User story and Requirement | As a Client, I want the system to be modular to facilitate the addition, removal, or replacement of modules without affecting other parts of the system. | The system should be designed to be modular
QA-7 | Secure password |  | A guest creates an account when the system is in normal operation. The Password Validation System responds by checking the strength of the inputted password. If it is not strong enough, it requests the guest for a new password. To measure the response, it checks if all the passwords accepted are strong passwords. | Overall, Django, Laravel, and Spring have built-in password validation systems that can be customized as needed. They also have built-in tools for measuring response times and debugging performance issues. Express and Ruby on Rails do not have built-in password validation systems, but they can be customized to handle this functionality. | ---- | Pipeline architecture
User story and Requirement | As a Guest, I want to be able to register a new account with a secure password | The system should be able to ensure that a given password is secure or not
QA-10 | Up time (Availability) |  | The system's software fails/crashes in normal operation. The system responds by entering a previous safe state. To measure the response, it checks if the restart occured in less than 1 minutes after the initial crash. | To measure the response and ensure that the system can quickly recover from a failure or crash, it is essential to consider the fault tolerance features of each framework. Spring, Django, Laravel, and Ruby on Rails all offer built-in fault tolerance features, while Express requires additional third-party libraries and modules. However, the specific fault tolerance features and configuration may differ between frameworks. | MySQL, PostgreSQL, and Oracle all have relatively mature mechanisms for recovery, such as replication and clustering, which can provide high availability and reduce downtime. MongoDB and Redis have similar mechanisms, but they are less mature and have some limitations. | Fault tolerance and reliability are the main concerns. A microservices architecture or service-based architecture can be beneficial since these architectures can provide fault isolation and allow for components to be restarted independently, reducing the chances of a full system failure. Additionally, event-driven architecture can help in quickly detecting and responding to system failures by triggering appropriate actions in real-time.
User story and Requirement | As a Client, I want the platform to be online 99% of the time | The system should be up at least 99% of the time per year
QA-12 | Video loading time (Efficiency) |  | The user finds a video with the system in normal operation. The system responds by automatically starting the video. To measure the response, it checks if the starting time was less than 2.5 seconds. | All of these frameworks (Spring, Django, Laravel, and Ruby on Rails) can handle serving media files such as videos and automatically starting them when a user accesses the system. They also include built-in tools for measuring response times and optimizing performance. | For this scenario, the choice of database may not be as critical as other factors such as the video encoding, network bandwidth, and server performance. However, some databases may be better suited than others for storing and retrieving video metadata and related information. A database that is designed for high throughput and low latency, and that can scale horizontally to handle concurrent requests, can help ensure that the system can respond quickly and handle the expected load. Cassandra- is a distributed NoSQL database that is designed for high throughput and low latency. It is optimized for write-heavy workloads and can scale horizontally to handle large volumes of data and concurrent requests. MongoDB- is a document-oriented NoSQL database that is designed for scalability and high availability. It is optimized for real-time applications and can handle a variety of data types, including video metadata. Amazon DynamoDB- is a fully managed NoSQL database that is designed for high throughput and low latency. It can scale automatically to handle large volumes of data and concurrent requests, making it a good choice for real-time applications such as video streaming. | A pipeline architecture or event-driven architecture could be suitable for this scenario, as they are designed to handle a high volume of requests and respond quickly. Microservices architecture could also be a good choice as it allows for individual services to be optimized for performance, but may be overkill for a simple video starting scenario.
User story and Requirement | As a User, I want the videos to load quickly | The system should load the videos in less than 2.5 seconds
QA-13 | Transaction time (Usability) |  | The user makes a transaction when the system is in normal operation. The Transaction system responds by processing the transaction and sending the user feedback about the transaction's current state. To measure the response, it checks if the transaction does not take longer than 30 seconds to be executed. | Spring and Ruby on Rails are the best choices for applications that require high-performance transaction processing and fast feedback to users. Both frameworks offer robust support for transaction processing and provide a wide range of features that can be used to optimize performance. However, Django, Laravel, and Express may be suitable for smaller-scale applications or applications that do not require high-performance transaction processing. | For a transactional system that requires fast response times and high reliability, a relational database management system (RDBMS) would be a good choice. RDBMSs are designed for transaction processing and can ensure data consistency, integrity, and durability.Oracle- is a powerful RDBMS that is used in many large-scale transactional systems. It is known for its robustness, scalability, and reliability, and can handle large volumes of data and concurrent transactions.Microsoft SQL Server- is a widely used RDBMS that is popular in enterprise environments. It is known for its high performance, scalability, and availability features.PostgreSQL- is an open-source RDBMS that is known for its reliability, robustness, and extensibility. It is designed to handle complex transactions and can be used in a variety of applications. | A service-based architecture or microservices architecture would be a good fit. These architectures allow for the Transaction system to be developed as a separate service or microservice, which can be scaled and optimized independently from the rest of the system. The use of asynchronous messaging and distributed processing can also help to improve the performance and reliability of the transaction processing. Additionally, proper load balancing and fault tolerance mechanisms can be implemented to ensure that the system can handle a high volume of transactions and minimize any potential downtime or service disruptions.
User story and Requirement | As a User, I want to receive feedback quickly from my transactions | The system should abort any transaction that takes longer than 30 seconds.
QA-14 | Backup of data (Integrity) |  | The user changes its data to the system when it is in normal operation. The system responds by backing up the changes in the database. To measure its response, it checks if the data is correctly saved and it is void of corrupted information. | Spring and Ruby on Rails are the best choices for applications that require high-performance database transactions and data integrity. Both frameworks provide robust support for database transactions and offer a range of features that can be used to optimize performance. However, Django, Laravel, and Express may be suitable for smaller-scale applications or applications that do not require high-performance database transactions. Ultimately, the choice of framework will depend on the specific requirements and constraints of your application. | MySQL and PostgreSQL are both traditional relational databases that provide strong data consistency and transaction support, making them suitable for applications that require data integrity. They both have backup and recovery mechanisms to ensure data is saved correctly. Cassandra is a distributed NoSQL database that provides high scalability and availability. It is designed for applications with large amounts of data and high write throughput. Cassandra has built-in replication and backup features to ensure data integrity. | A layered architecture or a service-based architecture would be appropriate. In a layered architecture, the data access layer can handle data storage and retrieval while the application layer handles user input and data manipulation. In a service-based architecture, the user data can be handled by a separate service responsible for managing and storing user data. Both architectures can ensure that the user's data is saved correctly and free of corruption.
User story and Requirement | As a User I want my data to be backed up | The system should have database replication
QA-17 | Sustain an annual user growth of 10% (Scalability) |  | A user uploads content to the system when it is running in normal operation. The system responds by handling the growth in content in a scalable and controlled manner. To measure the response, it checks if there is any downtime or side effects on the system. | Spring and Ruby on Rails are the best choices for applications that require very high levels of scalability while ensuring the stability of the system. Both frameworks provide robust support for building scalable applications and offer a range of features that can be used to optimize performance. However, Django, Laravel, and Express may be suitable for smaller-scale applications or applications that do not require very high levels of scalability. Ultimately, the choice of framework will depend on the specific requirements and constraints of your application. | MongoDB is a popular NoSQL document-oriented database that is known for its scalability and flexibility. It is good for handling unstructured or semi-structured data, and is designed to scale horizontally across multiple machines. This could be a good choice for a system that requires high scalability. Oracle is a widely-used relational database management system that is known for its scalability, security, and high availability. It is often used in enterprise-level applications that require robust and reliable data management. | Event-driven architecture and space-based architecture
User story and Requirement | As a Client, I want the system to be able to sustain an anual growth in users of 10% | The system should be able to whitstand an anual growth in users of 10%
QA-19 | Verifiability |  | The testers test the system when it is in normal and testing operation. The system responds by allowing components to be tested individually, making it easier to test. To measure the response, it checks if all the components can be tested independently. | All of the frameworks: Express, Django, Laravel, Ruby on Rails, and Spring, support the separation of components in a way that allows for individual testing. Therefore, they are all suitable for this scenario, and there is no clear winner among them. | --- | This could be achieved through a microservices architecture or a service-oriented architecture. Both of these architectures promote modularity and allow for services to be tested independently, making it easier for testers to isolate and identify issues within the system. Additionally, these architectures provide a high level of flexibility, making it easier to update and modify individual services without affecting the rest of the system.
User story and Requirement | As a Arquitect, I want to design a testable application | The system should be designed so that the components can be tested in isolation
Frontend
|  |  | Scenarios | Framework
TC-2 | Mobile application and web browser availability |  | ---- | Web There are several frontend frameworks available for our project. After considering the requirements, we determined that React would be the ideal choice due to its advantageous characteristics. React is a declarative programming model which simplifies the process of building UI components, as developers only need to specify what the components should appear like under each state. This reduces bugs and makes the application easy to understand. Furthermore, React's component-based architecture facilitates reusable UI components that can be combined to construct complex UIs. Additionally, React utilizes a virtual DOM, providing quicker updates and improved performance when the state changes. Moreover, a rich variety of tools and libraries are at hand in its vibrant ecosystem for creating intricate applications - including Redux and MobX for handling state management, Material UI and Ant Design for designing UI components; among many other options. Lastly, with an extensive community of developers backing it up, various resources are available for learning and problem solving. Despite the presence of similar features in other frameworks, we opted for React due to developers' familiarity with the framework, JavaScript, JSX, and other related technologies. Mobile Similarly, with the web frontend selection, there are several frontend frameworks that could be chosen for the mobile development of our project. Considering the requirements, we believe that React Native would be the best choice due to its characteristics. React Native enables developers to create cross-platform applications with a single codebase, reducing development time and cost. It provides code reusability across platforms, improving user experience consistency. React Native's hot-reloading feature speeds up the development process while its developer community offers an extensive selection of resources and support for faster implementation. Similarly, with the choice of web development, there were several other frameworks that had the same advantages as React Native for mobile development. Taking this into consideration, we ultimately chose React Native due to our familiarity with the framework.
| As a Client, I want to have my application available both on mobile and on a web browser | The system should be accessible to users from a mobile application and a web browser

## Relations
PL2 - PetPeople
Architecture Significant Requirements |  | Architecture elements |  | Traceability
Req ID | Req Name | Arch ID | Arch Name | How (ASR->ARCH) | Why (ARCH->ASR) | Comments
QA-1 | Correct emails | A26 | (AA) Security Component | A Security Component is available to authenticate the validity of the provided email. This component performs a check on the database to confirm if the email is already in use, and if it is, the creation of a new account is denied. Furthermore, it conducts a verification process to ensure that the email is legitimate. | We opt for the security component to guarantee the accuracy of emails. This decision is based on the robust features of the Express Validator library, which offers validator and sanitizer functions that can effectively validate the authenticity of an email. Additionally, we will utilize external email systems to corroborate the legitimacy of the email.
QA-2 | Secure payment | A61 | (PCC) Payments Facade | By putting in place a number of security mechanisms, the Payments Facade makes sure that the system transfers transactions to the correct seller without any eavesdroppers. With payment authentication, transaction controller and communication controller we can confirm the legitimacy of the payment data as well as the seller's identification, direct the money to the appropriate seller (preventing its interception or modification by outside parties), and even encrypt payment data. | The payment authentication component plays a critical role in maintaining security by implementing robust authentication mechanisms to prevent unauthorized access to sensitive data. Additionally, it employs two-factor authentication to reinforce our security measures. To ensure maximum security, all communication between the system components and the external payment system is encrypted. For secure communication, we use SSL/TLS encryption protocol to safeguard all transmissions.
QA-3 | Secure messaging | A53 | (MC) Secure Communication Component | The Message Controller handles message communications made through the PetPeople application. As soon as a client wants to send a message to a recipient, the "Client communication component" takes care of sending that message to the server, but before that the message goes to a component called "secure communication controller" that encrypts the message so that it is sent and stored in the database securely. The same happens for the inverse process, sending a message. | To guarantee secure communication, this component employs both SSL/TLS encryption and end-to-end encryption. With end-to-end encryption, only the intended recipient can access and read the message as the decryption keys are exclusively held by the sender and receiver. This makes it almost impossible for any third party to intercept and read the messages, thus ensuring maximum message privacy and security.
QA-4 | Easy maintenance (Modifiability) | A1 | (Dep) Version Control Manager | The Version Control Manager exists to manage incoming updates in order to cause minimum downtime possible. It will perform staged updates to the various VMs in the system, while also providing a repository with all the past changes made to the system. | In order to assure that no down time occurs when updating the system, the VCM makes use of a Deployment Control Script (DCS). The DCS is responsible for choosing the next machine at which an update will be implemented. In the case of the presented architecture, there are 2 VM's. It choses, for example, VM1 to update, leaving VM2 untouched. All traffic will now be directed to VM2. When VM1 finishes updating, the DCS will start to update VM2 and the AWS Load Balancer will now redirect all the traffic back to VM1. When VM2 finishes its update, the load balancer can share between VM1 and VM2. This implementation should make it so that there exists virtually no downtime.
QA-5 | Documentation (Modifiability) |  |  |  |  | Not guaranteed by the architecture. The developers should have a protocol that they follow when developping the application, which obliges them to document their code
QA-6 | Modularity (Modifiability) | A1 | PetPeople App | The overall architecture of the PetPeople App are designed to be modular to facilitate the addition, removal, or replacement of modules without affecting other parts of the system. | Service-based architectures are well suited to achieving modularity. By splitting the platform into smaller, independent services, the expected modularity was achieved.
QA-7 | Secure password | A24 | (AA) Register Controller | The "Register controller" is the component that handles the registration of a new user in the system. The controller verifies that all the necessary fields are in accordance with the platform's rules and only allows the registration process to end if so. Regarding the password, it must contain more than 8 characters, at least one lowercase letter, at least one uppercase letter, at least one number and at least one symbol. | This component uses the "zxcvbn" library for Express.js to estimate the strength of a password based on common patterns, providing users with feedback. Additionally, this component enforces a requirement that user accounts can only be registered with strong passwords.
QA-8 | Recover access | A25 | (AA) Account Recovery Controller | The "Account Recovery Controller" is the component that allows you to recover access to an account. After the user enters the email of the account to be recovered, the "Account recovery component" uses the "Notification Controller" in order to send an email to the associated email so that the user can reset his account password and regain access. | -----
QA-9 | Multi-language | A14 | PetPeople UI | The PetPeople UI will have an UI element where it will be possible to change the language of the platform. Initially the platform will support Portuguese and English and later will add more languages. | -----
QA-10 | Up time (Availability) | A72 | (Dep) AWS Load Balancer | The AWS Load Balancer chooses the best Web API VM to run from. In the case of failure it can quickly switch to a functional Web API VM guaranteeing in this way that the up time is close to 99% | AWS Load Balancer is a powerful and flexible load balancing solution that can help improve the performance, availability, and security of your application. Its tight integration with other AWS services and advanced features make it a popular choice for many businesses and organizations.
QA-11 | Cardholder information (Confidentiality) | A21 | Payment Controller | The Payment Controller guarantees that the user's cardholder information is not stored by discarding it after use. | The payments that go through the Payment Controller are all encrypted and no saves are ever made to the database. As such, there is no real way that the application stores the cardholder information.
QA-12 | Video loading time (Efficiency) | A30 | (CC) Bandwidth Controller | The bandwidth controller will control the video quality according to the user's bandwidth. In this way it is guaranteed that the video's loading time is adjusted to each user. | Since there is no way of controlling the user's bandwidth, this solution was found to be the best because it ensures small loading times in spite of a smaller or larger user's bandwidth.
QA-13 | Transaction time (Usability) | A61 | (PCC) Payments Facade | The Payments Facade will allow for a limited transaction time given that if the Transaction Controller takes longer than 30 seconds to complete a transaction it will abort it. Afterwards, the Communication Controller will inform the user that either the transaction was or wasn't successful. | Express.js was choosen for the handling of the Payments Facade due to the fact that it is built on top of Node.js which is a fast and efficient server-side runtime environment that can quickly communicate the information to the user.
QA-14 | Backup of data (Integrity) | A73 | (Dep) Replica Controller | In order to have the data backed up it is necessary to have a database where the data is stored. In addition, a replica controller can be added to certify the integrity of data. | Before choosing the Replica Controller, MongoDB was chosen has the query language to be used. It was prefered to use MongoDB over any other query language due to its flexible use, scalability, performance, ease of use and compatibility with today's applications. We used a Replica Controller due to the fact that it can guarantee that the user can always see its data even after the other database is not available.
QA-15 | Censoring of adult content (Safety) | A32 | (CC) Censor Controller | The Censor Controller is going to ensure that no user underaged can see any explicit or offensive content by calling an external system who uses an intelligent algorithm to censor uncalled for content. | This controller was chosen because it can, with the help of the Censor System, know when to censor content or not due to the technology built in the Censor System, which uses AWS Rekognition.
QA-16 | Update rollback (Survivability) | A74 | (Dep) Version Control System | By keeping all the different versions of the software, the version control system is able to easily roll back to a previous version of the software if need be. This is achieved with Git who can keep all the versions of the software. | We choose Git as the technology to be used since it is: 1. Open-source - Can be used by a variety of developers. 2. Speed - It is designed to be fast since it takes multiple snapshots of the system making it easier to retrieve previous versions of a file. 3. Distributed architecture - Every developer has a copy of the project on their local machine. 4. Flexibility - It can be used by small or large projects
QA-17 | Sustain an annual user growth of 10% (Scalability) | A1 | PetPeople App | Seeing that a Service Based Architecture is in use, there is good scalability. If there are a lot of users in the application, all that the system has to do is increase its server powers and/or add a new database / server. | The vertical and horizontal growth of the databases will allow for a better growth monitoring of the system ensuring in this way the scalability of the system. MongoDB technology is going to be used.
QA-18 | Usability | A14 | PetPeople UI | The central UI component (PetPeople UI) guarantees that at least 7/10 of Nielson's Heuristics are followed. PetPeople UI follows a rigid protocol that makes sure it adheres to as many of Nielson's Heuristics as possible in each view. It does this by organizing the views' information in a way that makes the user experience intuitive and responsive. | Due to PetPeople UI using React.js, which main advantages are simplified scripting and a component-based architecture, a more modular and intuitive design will be outputed. As such, it will be much easier to adhere to the Nielson's Heuristic than with other programming languages.
QA-19 | Verifiability | A1 | PetPeople App | The overall architecture of the PetPeople App allows for individual testing of each of the existing subcomponents, seeing that minimal coupling was implemented. | Each component in the architecture acts, mostly, independently, meaning that if we want to test a specific component, all the tester has to do is access that specific component and conduct the tests there. This allows all the other components to remain untouched, allowing for easier debugging in case that an error is detected.
QA-20 | Number of transactions (Performance) | A61 | (PCC) Payments Facade | The Payments Facade contains an orchestrator that allows for many transactions to occur at the same time with little to no consequences. The Payments Facade is composed of four components. To ensure that up to 1000 transactions can occur each minute, an orchestrator allows for fast request redirection. The workflow inside the Payments Facade component is the following: the payment goes to the Payment Authentication where it gets authenticated, then it goes to the Transaction Controller where it gets directed to the correct seller and gets encrypted and finally, it goes to the Communication Controller where it gets sent to the seller. | In the Facade, all of the components are executed asyncronously in order to allow for many transactions to be sent and so that there is little to no waiting either on the client's or the server's side. Due to the existence of a central orchestrator, there is an increase in scalability, making the system be able to handle more transactions and be able to tolerate spikes in traffic without compromising performance or availability.
QA-21 | First year | A75 | (Dep) Database Orchestrator | The Database Orchestrator ensures that there is enough space to accomodate for the first year user goals, this is, to support 1 million users. To accommodate a large amount of users, 1 database might not be enough and might become too filled to the point where it becomes slow. Due to this, multiple databases might be needed. As such, the Database Orchestrator serves to direct new information to the correct databases in order not to overwhelm one of them. In the first deployment, only 2 databases shall be installed, seeing that this amount should suffice for the target number of users. | An orchestrator was used seeing that it can increase throughtput and, in general, it increases scalability, making the system be able to handle more transactions and be able to addapt to the current traffic in the system. As such, it will be able to support an elevated number os simultaneous users without any major drawbacks.
QA-22 | Sustain an annual content growth of at least 200% in content (Scalability) | A75 | (Dep) Replica Controller | The Replica Controller distributes new data throught the various available databases, in order to not overwhelm a particular one, making the addition of new content more scalable. The Replica Controller attempts to distribute the data fairly among all of the available databases. As said in the previous QA, when first deploying, only 2 databases will be installed. If more are needed, they can easilly be added to the orchestrators list. | An controller was used seeing that it can increase throughtput and, in general, it increases scalability, making the system be able to handle more transactions and be able to addapt to the current traffic in the system. As such, it will be able to support an elevated number os simultaneous users without any major draw backs.
QA-23 | Number of concurrent requests (Performance) | A72 | (Dep) AWS Load Balancer | The AWS Load Balancer decides the best Web API VM to run from and in the case of failure it can quickly switch to a functional Web API VM. When accepting incoming traffic from clients, the AWS Load Balancer, routes them to an available system. It also monitors the health of the systems, ensuring that new traffic only goes to healthy systems. When an unhealthy system is detected, the load balancer stops all routing traffic to that system. When it becomes healthy again, the routting traffic may resume. This allows the system to have many simultaneous events without overwhelming any of the existing Web API VMs. | AWS Load Balancer is a powerful and flexible load balancing solution that can help improve the performance, availability, and security of your application. Its tight integration with other AWS services and advanced features make it a popular choice for many businesses and organizations.
QA-23 | Number of concurrent requests (Performance) | A27 | (DEP) AWS Load Balancer | The Request Orchestrator automates request redirection when there is need to display or save content. The Request Orchestrator can choose to redirect a request to one of three components. These components are the Upload Manager, responsible for uploading photos, videos and products; the Feed Manager, responsible for showing user feed (social network, marketplace and information hub); and the Search Controller, responsible for handling search requests. With this structure, the orchestrator allows for asynchronous calls to these components, allowing requests to flow quickly through the system, in this case, when content updates are requested. This is very important to not clog some of the components. | An orchestrator was used seeing that it can increase throughtput and, in general, it increases scalability, making the system be able to handle more transactions and be able to addapt to the current traffic in the system. This being said, it will support a large quantity of concurrent requests without the system suffering in performance.
QA-23 | Number of concurrent requests (Performance) | A62 | (PF) Payment Request Orchestrator | The Payment Request Orchestrator automates request redirection when an payment needs to be executed, making the process assynchronous and more efficient. When a request arrives, the Payment Request Orchestrator chooses between three components. The Payment Authentication, where a transaction gets authenticated; the Transaction Controller, where the transaction gets redirected to the seller and encrypted; and the Comunnication Controller, where a transaction gets sent to the seller. All of these functions are executed asyncronously, making the process efficient, fast and secure, allowing for many requests to be processes at the same time. | An orchestrator was used seeing that it can increase throughtput and, in general, it increases scalability, making the system be able to handle more transactions and be able to addapt to the current traffic in the system. In this case, the Payment Request Orchestrator allows for multiple simultaneous payment requests, allowing for multiple buys to occure at the same time, while a minimal amount of transactions fail to go through.
QA-23 | Number of concurrent requests (Performance) | A66 | (NCC) Notification Orchestrator | The Notification Orcherstrator automates notification requests, sending messages either through email, through the platform or via SMS. This orchestrator allows for various notification requests to be responded simultaneously. | Again, an orchestrator was used for the same reasons as before. It increases trhoughput and makes the system more scallable. The Notification Orchestrator assures that multiple simultaneous requests of notifications are sent to the correct users via the correct system.
| 0 |  | #NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?